SBHC Patient Participation Group (PPG)

Action Plan/Tracker – August 2026

See Appendix for Acronyms (with hyperlinks)

| Date | What is the issue you have identified? | Where is the evidence? | What will you do about it? | What can’t you do and why? | How will you know it has been successful? | How will it improve the experience of the wider community? | Who will lead the project? | Completion date | PPG ACTIONS/ DECISIONS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nov 2026 | ANNUAL AGENDA ITEM: Patient Feedback | Patient Survey Results | Review information across all teams | N/A | There is a good response rate from patients [random or targetted sample?] | Allows changes to be made based on feedback from patients | Practice Manager | October 2026 | Review Patient Feedback Surveys ahead of November meeting |
| Aug 2026 | ANNUAL AGENDA ITEM: Complaints data | Good practice for PPG to have oversight | N/A | N/A | A summary complaints report is submitted annually to NHS England by the Health Centre. Any concerns would trigger a CQC inspection | Helps identify any trends in complaints – comparative data will be provided going forward | Practice Manager | July 2026 (PPG to remove from Action Tracker after August meeting) | Receive annual complaints data, re: assurance of no significant concerns in service delivery |
| May 2026 | PREVIOUS PPG SUGGESTIONS:See Annual Cycle of Business – Revisit in March 2027, eg Request a presentation, eg from Devon Carers, Dementia Support, Mental Health, etc.? Days/Timings? | Eg Free First Aid courses run by St John’s Ambulance Add CPR/ choking video to playlist of waiting room TV Communicate CPR courses in Village Hall | TBC | TBC | TBC | TBC | TBC | March 2027 | Discuss at March PPG Meeting |
| July 2026 | Lack of clarity around the transfer process from one Health Centre to another | New patient feedback | Improve information around this process on the Health Centre website | N/A | New patients will understand the transfer process, eg that their repeat prescriptions do not automatically transfer | New patients will enjoy a less stressful transfer process | Practice Manager | Nov 2026 | PPG to monitor at next meeting |
| May 2026 | The PPG offered a member to sit on future recruitment panels for staff at the Health Centre | N/A | To be discussed with partners | Attendance would be dependent on the role advertised | Feedback from all parties involved | Having a patient voice/representative when interviewing could allow for a different view point | Practice Manager Chair | ongoing | PPG to monitor any future PPG involvement in staff recruitment processes |
| May 2026 | The PPG offered member support, re: the mock CQC Inspection planned for June | N/A | As an informal visit this was not actioned, however it would be for a full inspection | Allow member/s to sit in on confidential conversations | Result of CQC inspection | In representing the views of the community and allowing members to share the process of a CQC inspection with the wider community | Practice Manager/ Chair | Ongoing | See update on August agenda |
| May 2026 | Consider flagging clients who may need support in communicat-ing their medical needs | Patient Feedback | Reasonable adjustments project started and being shared with all patients via a set number of question-naires being sent daily to all patients where communicat-ion needs can be document-ed on medical records | Change the questionnaire as it has been set by NHS England | Having recorded information on individual needs and wants on patient medical records | Meeting needs of individuals when possible | Practice Manager | August 2026 | PPG TO CONFIRM SATISFIED WITH THIS RESPONSE/ REMOVE FROM ACTION TRACKER: NB follow up email from PPG Member 28/07 – may need further monitoring by the PPG |
| May 2026 | Members suggested some information on ‘who to call when’ would be helpful for patients. | Patient Feedback | Ongoing project for team, looking at external resources to share in the surgery/ online/social media. | TBC | Patients will know who to call when, re: best meeting their needs, ie criteria for calling 999, 111, Minor Injury Unit, SB Health Centre or Pharmacist | More effective and appropriate use of local resources | Practice Manager | August 2026 | Staff to update with realistic timescale at meeting |
| May 2026 | Concerns that the reception team are ‘tri-aging’ patients | Patient feedback after the meeting | New Triage tool in place to allow patients to complete a form when requesting urgent / on the day appointments | N/A | Patients feel assured that ‘tri-aging’ isn’t happening from the reception team | The receptionists do not prioritise the appoinments, the triaging GP now does this | Practice Manager | August 2026 | PPG TO CONFIRM SATISFIED BY THIS RESPONSE/ REMOVE FROM ACTION TRACKER |
| April 2026 | An opportunity for the Dementia Alliance to visit the Health Centre to ensure it is Dementia Friendly | Request from the Parish Council | Invite the Dementia Alliance to assess the Health Centre for Dementia Friendly Signage | N/A | A Dementia Alliance visit has taken place and any recommendations implemented | To ensure a consistent approach throughout the village, re: dementia friendly signage | Practice Manager/ Chair | Update: August 2026 | PPG to monitor implementation |
| March 2026 | Geographical representat-ion of the PPG is limited | Observat-ion by a PPG Member | Targetted recruitment by the Chair and Health Centre | N/A | More PPG Members from outside South Brent/representatives recruited from each catchment area | Helps to ensure more patients are represented | Practice Manager/ Chair | Nov 2026 | Two Members have been recruited from Ivybridge since the March Meeting |
| July 2025 | Functionality of the NHS APP | Patient feedback | APP training and support is available from the Health Centre 1:1 appoint-ments can be booked in advance | NB Controlled centrally so cannot alter locally in a bespoke way | High uptake and use of the NHS App in our community | Easier access for patients to request items and complete admin tasks when the surgery is closed | Practice Manager | Ongoing monitoring by the PPG (standing item) | PPG Member has suggested possibility of doing some outreach training to specific community groups |

APPENDIX: ACRONYMS WITH HYPERLINKS TO MORE INFORMATION

| SBHC | South Brent Health Centre |
| --- | --- |
| PPG | Patient Participation Group |
| SD&T PCN | South Dartmoor & Totnes Primary Care Network |
| CQC | Care Quality Commission |
| SMS | Short Messaging Service (ie texts on mobile phones) |
| NHS APP | https://www.nhs.uk/nhs-app/help/ |
| HCA | Health Care Assistant |
| ICB | Integrated Care Board (replaced CCGs/Clinical Commissioning Groups in 2022) – for South Devon |
| ICB DPO | Integrated Care Board Data Protection Officer |
| CPR | Cardiopulmonary Resuscitation |